SUBFACTOR 4: CONTRACT MANAGEMENT PLAN

Company Structure

Miami Wiipica, LLC has a very streamlined organization, designed specifically to meet the service and delivery needs of IDIQ projects. Our philosophy is to maintain an organization that is flexible enough to expand and contract to meet the requirements of both large and small projects. We do this by regionalizing our staffing, developing localized project offices and providing decision-making authority at the lowest level possible. This allows us to be adaptable and provides for quick, efficient resolution of questions or issues raised by project stakeholders.

We have provided an organization chart to depict the working arrangement of our team; this chart illustrates how our team members fit into our overall corporate structure. The pages following the resource chart provide information about those who are filling our key corporate office management positions.

# Organizational Chart Narrative

# Corporate Level Roles and Authority

We have two levels of corporate management that support our Project Managers. The initial level is our senior management, consisting of Program Manager and General Manager, and our contract support staff (Safety Director, Quality Control Manager, Accounting, Design/ Build Integrator, Design Manager etc.). The people at this level provide corporate level proposal, design, contract administration, training, quality control, safety, labor, financial and management support to our on-site staff.

Our corporate office provides an important standardization function between all our field offices. It acts as a Program Management Office to ensure we consistently apply our well-defined processes and procedures across all projects.

The work done by the corporate office is designed to remove administrative concerns from the field offices, so they can focus more on the customer’s needs and on construction issues. If the on-site staff cannot resolve a concern, our senior management and corporate staff members provide the necessary support to quickly resolve concerns.

# Personnel/Key Positions Qualification

The highest level of corporate management is the Program Manager, Mr. Cecil Whitlock and General Manager, Harry Brown, Jr. Mr. Whitlock has final decision making and contractual authority (for changes greater than $10,000,000) to negotiate and bind the company on the basic contract and all task orders. Mr. Brown has decision making and contractual authority of up to $10,000,000.

As we prepare for design and/or construction task orders, we assign a Project Manager as the primary point of contact—to coordinate with our corporate staff and guide the efforts of our design and construction teams. The Project Manager is focused on the specific needs of the assigned task order(s).

Our Project Managers have the authority to make decisions that do not exceed the original cost parameters of a given task order. For task order changes that impact costs, our Project Managers will quickly consult with the client, senior management and/or the Program Manager to determine the best solution for all involved. When a decision is made, they then have the authority and responsibility to work with all necessary parties and contract officials to implement appropriate changes

# Design Roles and Authority

Our Project Managers work together with our Design Manager to integrate our design teams with construction professionals. Together, these managers have the authority to make design decisions. This integration is the most important aspect of our ability to solve design problems and perform at high levels as a Design-Build construction firm.

During all of our Design-Build projects, our team works together to understand and integrate the owner’s requests and expectations while staying within the contract cost limitations. As our team members review the drawings and make comments, we can integrate innovative thoughts and ideas into the project. This integration effort has produced huge dividends for our customers, as we are able to meet their requirements in both cost-effective and innovative ways.

This review and integration process has also provided a mechanism for us to control project risks. As we engage in open, transparent communication regarding project requirements and potential solutions with our customers and our team members, we are better able to control common Design-Build risks such as scope creep, cost growth, schedule impacts, resourcing issues and other problems that arise in a fluid Design-Build scenario.

# Construction (On-site) Supervision

Our Project Managers are ultimately responsible for all on-site construction and/or design-build supervision. However, we always provide these managers with appropriate on-site support, depending on the task order needs.

Depending on the requirements of the Task Order, our on-site staff may include four primary positions or responsibilities as follows:

- Project Manager

- Site Superintendent

- Site Safety Manager

- Onsite Quality Control Manager

If a task order requirement requests the site supervisor to perform dual duties, the Site Supervisor takes responsibility for QC functions. These key on-site personnel are augmented by other employees or subcontractors, as dictated by the needs and complexity of individual task orders.

Each project site will be assigned a Project Manager. This manager is the direct representative for the Corporate Office at the construction site. He or she has direct responsibility and authority for day-to-day sustainment, restoration and modernization decisions and project activities. The Project Manager is specifically responsible for acquisition of staffing, subcontractors, labor, resources, materials and facilities. He or she also directs, monitors, and controls all project work. The Project Manager is the hub for all project communication and is responsible for on-time, under-budget and high-quality completion of project work. Miami Wiipica believes these leaders are the best resource available for quickly solving project problems at the lowest level possible.

The Site Superintendent has the responsibility and authority to direct the efforts of subcontractors. Under the direction of the Project Manager, the superintendent follows up on the daily efforts of subcontractors, ensures subcontractor personnel are working safely and providing quality products, schedules subcontractor activities, resolves issues that arise between subcontractors, ensures subcontractors account for project risks, provides timely payment certification, and acts as a liaison between the subcontractors and the Project Manager.

A Project Safety Manager is assigned to monitor and control all safety activities on a given site depending on the requirement of the Task Order. He or she is directly responsible for implementing our corporate safety program on site. As part of these duties, he or she will implement effective Accident Prevention Plans, Activity Hazard Analyses, Risk Assessments, Interim Life Safety Plans, and many other safety requirements as stipulated in individual task orders.

Finally, Construction Quality Control Manager (CQCM) ensures that all work completed on the project is done in accordance with corporate and U.S. Army Corps of Engineers (USACE) project quality requirements. These managers understand the critical nature of working within occupied facilities or on busy installations. The CQCM is responsible for ensuring prime and subcontractors adhere to all quality requirements outlined in individual task orders.

We perform a complete and in-depth evaluation of task order complexity, size, coordination and requirements to determine the success parameters for each project. In the event that the task order requirements or our in-depth evaluation do not specifically call for dedicated on-site Quality Control or Safety Manager, these responsibilities would fall on the shoulders of the

Project Manager and Site Superintendent. All of our Project Managers and Site Superintendents are quality and safety trained per contract requirements.

# Subcontractor Management

The final element of our proposed organization includes subcontractors of multiple trades. These subcontractors are all under the direct supervision of the Project Manager and focus on providing the professional services for which they are contracted.

The Miami Wiipica team prides itself in its ability to ensure its relationship with each subcontractor is seamless. We will not make our problems your problems. We do this by selecting the best subcontractors for the project and carefully managing our professional relationship with each subcontractor.

Experience / Capability

Miami Wiipica LLC, a SBA certified tribal 8(a) owned by the Miami Nation Enterprises, is proud to present our proposal for the Multiple Award Construction Contract (MACC) for Joint Base Andrews, MD and Joint Base Anacostia Bolling, Washington, D.C. The Miami Nation Enterprises has built a family of businesses spanning the construction and technology fields serving customers across America. Miami Wiipica leads an experienced and truly integrated Team of design professionals and experienced general and specialty subcontractors. Our Team is dedicated to supporting the program mission by providing responsive and reliable facilities in support of the mission.

We offer the following key benefits:

- Knowledge of renovations, alterations, and new construction for the Federal Government: At Miami Wiipica, our singular focus is to provide design/build, repair and new construction services to improve our Nation’s aging federal facilities. The team has successfully completed multiple repair, renovation and construction projects for the federal government.

- Sustainability and Efficiency: Miami Wiipica will achieve sustainability, as well as significant cost savings, by designing and installing efficient, modern, building systems. Our team will provide the best long-term value by performing appropriate energy modeling and life cycle cost analyses. We will provide teams that are experienced in sustainable design and construction to ensure the required savings and long-term value are realized.

- Collaboration: The Miami Wiipica Team ability to collaborate with our partners and stakeholders, will ensure quality, efficiency, timeliness, and cost savings on every project.

- Participation in Multiple Award Construction IDIQ Contracts: Multiple Award Construction Contracts (MACC) are the staple of our business. We have extensive knowledge of the requirements and processes required under such contracts.

- Ability to Manage Numerous Projects at Various Locations: Our past performance has demonstrated our ability to manage a multitude of projects at various locations across the country.

- Safety: We pledge to continue our record of safe performance on all our projects, implementing infection control and Interim Life Safety Measures as required.

- Client Satisfaction: Our primary goal is to please our clients. Through our knowledgeable Construction Project Managers, our seasoned Architect/Engineer Teams, and our numerous partners and subcontractors, we will complete projects within time and budget. Our Quality Control Program ensures that we strive to meet all project requirements to the satisfaction of our customers.

# OVERVIEW OF PLANED CONTRACT EXECUTION

# Contract Execution Plan

# Responding to Task Order RFPs

We combine the efforts of every key member of our organization to successfully respond to a task order RFP. Every task order, no matter how large or small, is important to us as we continue to build a trusting, performance-based relationship with our stakeholders. As such, we are committed to respond to every task order opportunity offered as a result of this contract.

Task orders can be developed in one of two ways, both of which allow us to respond rapidly to the requirements. One option available to the Government is the issuance of an award without competition. Under this option, a member of our Management team communicates with the Contracting Officer Representative (COR) to coordinates a site visit and/or develops an understanding of the desired project scope. The government then develops formal RFP and proceeds to negotiation and award. The other option is for the government to issue a competitive RFP that includes a scope of work. This is usually followed by a site visit with the COR and other Government representatives.

Under either procurement path, our management team assigns a Project Manager to lead the proposal effort. This assignment is based on project size, complexity, and location. The Project Manager then forms a Request for Proposal (RFP) Response Team that is designed specifically to provide a rapid, effective response to a task order RFP. Our response teams consist, at a minimum, of a Project Manager, an Estimator, an Administrative Assistant and Construction Team members. A Design Team member is included if the RFP requires a design. Our response teams also integrate home office assets who can assist with estimating, preparation, submission and negotiation.

During, the initial phase of preparing an RFP response, the team works directly with the home- office support staff and appropriate government representatives to clearly define the project requirements and success parameters. We visit the site to collaborate as much as possible with the COR and other customers; this allows us to gather information and historical facility data to ensure we fully understand the project scope. On complex projects, and where it is beneficial, our team of qualified Designers (which we have worked with for years), Design Managers and Construction Managers will prepare schematic designs and preliminary space plans—to define the scope of the project and convey this information to subcontract bidders. The goal is to reduce uncertainty with the bidders so that we obtain complete, competitive bids.

Once we fully understand the task order scope, the Project Manager works closely with the assigned Estimator to identify local subcontractors who can meet the scope requirements. They specifically identify local small businesses that possess the skills required by the task order.

The Project Manager leads the team as it communicates with potential subcontractors, receives bids, selects contractors who present the best value to the government, estimates self-performed work, and integrates design (if required) and constructability information into the final estimate. The home office staff provides a final check of the estimate to ensure the RFP Response Team has met all of the estimating requirements.

With a proper understanding of scope and a good estimate in place, the Project Manager leads the team as it prepares the final response. Every member of the RFP Response Team participates in preparing answers, generating documents, identifying solutions and meeting Government requirements in our responses. The team then works with the home office staff to integrate narrative, documents, estimates and other important information into a cohesive, comprehensive response that is ready for review by the Government. The narrative will be developed with sufficient detail to convey a clear understanding of the requirements. We will provide timelines and critical path items to achieve the desired period of performance provided in the RFP.

We understand the importance of following directions during any RFP response process. Thus, we always submit our responses in accordance with the requirements listed in each task order RFP. In doing so, we ensure that our responses are timely and delivered to the appropriate person or office as outlined in each task order RFP. We understand that our proposal will be evaluated using a low price technically acceptable or low-price approach. All our proposals will be prepared to address the technical approach for the individual task order; past performance of similar type of projects within 5 years of proposal date; period of performance; and cost.

When the Government selects our task order RFP response for further discussions , our home office provides personnel who will negotiate the final contract parameters. The Program Manager, or his designated representative, has the authority to negotiate on behalf of Miami Wiipica. We always seek to satisfy our Government customers, while also considering the business aspects of being able to produce a successful project.

To provide continuity and a single interface to our client, our RFP Response Team will be the same team that will execute the assigned task order through its successful completion.

Involvement of the execution team throughout the RFP response process is fundamental to the success of Miami Wiipica projects.

Multiple Award Construction Contract (MACC)

Figure 02 - Work Order Flow Chart

# Work to be Self-Performed

We self-perform tasks during Pre-Construction, Construction and Closeout phases as described in the paragraphs that follow.

Pre-Construction Phase on Design-Build Projects

We have the in-house capability to perform preconstruction and design functions as necessary. We assist customers with project development, definition, and approval processes. We provide feasibility studies, site surveys, and work plans—complete with all design documents and specifications. We work closely with our customers to ensure that all of these documents are approved and ready for construction award.

Construction Phases

During construction we have the ability to self-perform many different types of tasks. We have listed some of these below.

  - Project Management

  - Incidental Design

  - Construction Administration

  - Quality Control

  - Infection Control

  - Safety and Security Management

  - Equipment Planning

  - Equipment Procurement

  - Transition Planning

  - Other Functions

    - General Trades

    - IT Networking/ Cabling

    - Audio and Visual System

    - Security Systems – Alarm System and Physical Barrier

    - Modular Structures

Miami Wiipica, LLC is part of the Federal Contracting Group (FCG) and contained under the FCG family of companies. Miami Tribal Systems Integrators, LLC, which is a low voltage integrator & contractor and Champion Commercial Fence Builders, a fencing and security company, are used when it makes economic sense for the project and the Government to self- performance these major specialty trades for projects, reducing coordination obstacles and overall costs.

Closeout Phases

Our capabilities do not end when construction is complete. We are also fully invested and committed to the successful turnover of our projects. We provide excellent operation and maintenance documentation; training and develop accurate Computer Aided Design (CAD) as- built drawings.

Additionally, we work with the appropriate stakeholders to effectively close all contractual requirements. At the end of each task order we commission the systems we have placed within the facility, meet all testing requirements, close out all punch-list items and achieve proper acceptance of our work; we also warranty our work and stand by our warranties. Our capable on- site staff is trained to provide an exceptional level of service through these processes by solving problems on-site at the lowest level possible.

Corporate Support

From start to finish of each project, our corporate office provides excellent proposal, design, contract administration, training, quality control, safety, labor, financial and management support to our on-site staff. Much of the work done by the corporate office removes administrative concerns from the field offices, so they can focus more on the customer’s needs and on site- specific design and construction related issues.

Conclusion

As shown in this discussion, our self-performance capabilities are extensive. However, our intent in every project is to do what is right for our clients.

We fully believe that the amount of work we self-perform should be dictated by the specific needs of a given task order. We are committed to self-performing many functions under this contract and to meet and exceed the require percentages. However, if it is more economical to use local tradesmen for the benefit of the customer, or if it is better for the project to integrate small businesses, we intend to be flexible with the amount of work self-performed.

# Managing Subcontractor Acquisitions

Miami Wiipica has relationships with many subcontractors, including pre-qualified small and disadvantaged businesses. We have established practices and procedures to process and track subcontractor staffing and performance, invoicing and payment. Our subcontract management relies on formal agreements, proper pricing, and integration of subcontractors into a seamless team. Our subcontractors undergo a thorough pre-screening and pre-qualification process that ensures us of their capabilities, business size and financial stability. During the proposal process, our estimating team and project managers communicate extensively with every potential subcontractor during each of the following phases of procurement.

Pre-Bid

Our subcontractor selection process is task order driven. Upon receipt of a task order RFP, we follow an extensive evaluation and selection process to ensure we provide opportunities to the right subcontractors.

During this phase we contact the required trade subcontractors from our prequalified list. All invited trade contractors are provided an Invitation to Bid with a complete procurement package.

Our Project Managers and Estimators spend considerable time walking subcontractors through our processes to ensure they have a complete understanding of the project details, including:

- Scope of Work requirements

- Place of performance

- Required format of proposal

- Due date(s) for proposals

- Discipline(s) needed

- Government terms and conditions

- Federal Acquisition Regulations (FAR) and other contractual parameters

- Project Manager and Estimator contact information to provide bidding assistance

- SBA Contact(s) who can address FAR and small business questions

- Notification of site visits, amendments and/or extensions

Pre-Award

We invite no less than three (3) subcontractors to compete on each scope of work. The subcontractor that is deemed to be the best value based upon a combination of capability and cost is used in our bid to the Government. During this phase we prepare our subcontractor’s agreement indicating the quality process to be used in our projects; we also ascertain a subcontractor’s ability and willingness to use our Quality Control process and Safety Plan

Contracting

We spend extra time (after we have been awarded a contract) to ensure that our subcontractor’s scope and quality match our expectations, prior to finalizing a subcontract award. We find this final step prior to the subcontract execution to be valuable in terms of meeting expectations during the project.

Administration

The Miami Wiipica team prides itself in its ability to ensure its relationship with each subcontractor is seamless when viewed by its customers. We will not make our problems your problems. We do this by selecting the best subcontractors for the project and carefully managing our professional relationship with each subcontractor company.

Our best value selection process lays the groundwork for our critical relationship with each of these subcontractors. We approach the relationship with all our subcontractors in a professional and effective manner. Throughout this relationship, we ensure every subcontractor understands the project requirements and executes accordingly. In the event of a dispute or a problem raised on a project by a subcontractor, we work to resolve those disputes in a manner that is transparent. On past projects, we have resolved subcontractor related issues without disrupting critical schedules or creating unnecessary costs for project stakeholders.

Execution

We conduct daily inspections to assure continued quality control among our subcontractors. We also ensure proper compliance with workmanship requirements as established in the design documents , specifications and approved submittals. We review and establish all task information and installation procedures in preparatory meetings and initial inspections. We ensure that materials are inspected upon arrival on site to confirm compliance with approved submittals. We also inspect materials during installation for verification against specifications and to ensure they are installed in accordance with the manufacturer’s instructions. Daily inspections verify subcontractor workmanship in accordance with the acceptable standards.

Finally, we ensure that all building systems installed or modified are tested and witnessed (as required), with the required functional performance documented on the Quality Control Daily Report.

Deficiencies

We track all subcontract work on a Deficiency Log throughout the life of the project until the closeout Punch List is prepared. It is also a key component of quality management on each project. The list contains those QC issues observed by the QCM that were not addressed the same day. This list describes the work to be corrected, the day a deficiency is observed, who is responsibility for correcting the deficiency and the date the correction is made.

The Quality Control Officer shares this report with trade subcontractors to provide timely follow-up on each item.

Conclusion

We have extensive experience managing subcontractors, we understand the local subcontractor labor pool and understand how best to manage the relationships with these key team members.

# Steps Taken After Award of a Task Order

This section outlines the technical approach Miami Wiipica uses in planning and executing construction or design/build task orders. The approach described below has been refined and improved through the successful execution of multiple projects. In this section, we assume that the steps taken after award of a task order can be divided into three major categories: Pre- Construction, Construction, and Closeout. These sections are visually diagrammed in the Task Work Order Flow chart on Figure 02.

Pre-Construction Steps on Design Build Projects

After we receive contract award and notice to proceed from the Government, we enter the Pre- Construction Phase. Work schedules will be prepared and submitted within 5 calendar days. The schedule will be in accordance with instructions pertaining to AF Form 3064, Contract Progress Schedule, and AF Form 3065, Contract Progress Report. This phase typically begins with a Pre- Construction Conference, during which we discuss task order requirements with Government stakeholders. This conference marks the beginning of the physical design and or construction work that will be performed during the task order.

Each and every design begins with a review of the project scope to fully understand the requirements of each particular project. Each discipline reviews the most current codes, regulations or other guidance related to their design or design-build responsibilities and provides a list to the design manager. These requirements are also crosschecked with the preconstruction team at the initiation of design to ensure project planning and design are melded together into a compliant project. This project specific compliance checklist follows the design and design

submittals through construction to ensure a code compliant process and project. The design and construction will comply with the versions of the following references that are current at the task order award:

  - Unified Facilities Guide Specifications (UFGS).

  - Unified Facilities Criteria (UFC) and Facilities Criteria (FC).

  - Air Force Corporate Facilities Standards (AFCFS).

  - Air Force Prototypes and Standard Designs.

  - Air Force Design Guides and Standards.

  - Air Force Guides, Handbooks, Instructions and Pamphlets.

  - Air Force Engineering Technical Letters (AFETL).

  - Corps of Engineers Manual, EM 385-1-1

  - Occupational Safety and Health Administration (OSHA) General Industry Safety and Health Standards (29 CFR 1910), Publication V2206. 29 CFR 1910

  - OSHA Construction Industry Standards (29 CFR 1926).

  - National Emission Standards for Hazardous Air Pollutants (40 CFR, Part 61).

  - Hazardous Materials: Refer to hazardous and toxic materials/substances included in Subparts H and Z of 29 CFR 1910 and to others as additionally defined in Fed. Std. 313.

  - Base Governing Standards ( Attachments 1 -9)

Every design team is also supported by an independent design commissioning team that serves as our internal review prior to each design submittal. The design commissioning team is comprised of senior architects and engineers not involved in the particular design who “shadow” the project design process for compliance and quality. The checklist of project specific relevant codes or regulations compiled by the design manager is back checked by the design commissioning team prior to each design submittal.

At the beginning of the Pre-Construction Phase (when the task order requires us to perform design services) we typically perform a formal Site Investigation. We know that an accurate, effective Site Investigation is the basis for providing a timely, quality product in an efficient manner. It is also a foundation for a cooperative working relationship between Miami Wiipica professionals, the Command, the Facility Managers and Government Project Management Teams. A good Site Investigation validates the desired scope, the facility and end-user requirements, and it identifies problems and proposes solutions for which a consensus can be established.

We approach the Site Investigation/Report as the cornerstone from which the Design is developed and upon which the project is built. Thus, it is essential that the survey team be comprised of personnel with appropriate design and construction experience. We also believe that the Facility Management Staff and end-users are experts in their fields, and therefore must be full participants in the entire process. Their critical input and vision must be valued and used in identifying problems the design team will solve. They are encouraged to assist with solutions to all problems.

A Site Investigation is an important vehicle through which all of these professionals can communicate and coordinate the scope and feasibility of the project.

A good Site Investigation includes the following activities:

- A formal briefing with all key stakeholders

- A walk-through of the project site to investigate each of the problem areas stated in the task order

- User interviews to confirm or develop the Program for Design and to determine functionality, workflow and room relationships within the facility

- Meetings with the Infection Control Risk Assessment Committee to identify containment and infection control requirements

- A complete architectural and engineering survey of the spaces considered for renovation and ancillary support areas and systems.

- Interviews with Maintenance and Facility Staff to identify known or potential problems within the renovation area

- Preparation of a site description, a hazard risk analysis, a site control document, and a site disruption plan which itemizes actual, probable, and potential disruptions to installation operations along with recommendations to reduce the effects of unavoidable interruptions

- Meetings with Post entities such as Master Planning, Director of Information Management, the Fire Marshall, Physical Security and Antiterrorism / Force Protection representatives

- Reviews of existing Hazardous-Material Surveys, combined with visual surveys (and appropriate sampling and testing) of the renewal area for hazardous materials. Hazardous materials to include but not limited to ACM, LBP, mold, mercury and other known environmental contaminants.

- As-Built Verification of Government provided information.

- Development of budgetary cost proposals for the scope elements listed in the task order

- Production of a Site Investigation Report as required by contract

Upon completion and approval of the Site Investigation, the Project Manager will lead the design team through design development.

All design efforts required by a task order will be executed under the direction of a Design Manager, through our long-term teaming Architect/Engineer, DBC|KSA. These designers will ensure that all proper internal controls and review procedures work to eliminate conflicts and errors or omissions. They will also provide Design Quality Control (DQC) to ensure the technical accuracy of all designs.

Upon receipt of NTP, the design team uses the information developed during the Site Investigation or from other scope documents to begin development and refinement of the design. The function of the Designer of Record (DOR) for each discipline is to diligently progress through the design phases toward a complete and coordinated multidiscipline set of documents to be submitted for review and approval.

The role of the Design Manager during this phase is to keep abreast of the design progress, to ensure the Design Quality Control (DQC) representatives for each discipline are checking and signing off on designs, to complete constructability reviews, to procure any missing information, to keep the design on schedule and under budget, and to advise the stakeholders of any issues that need resolution. Constructability and Communication are critically important processes involved in successfully completing the design.

The Miami Wiipica approach to a successful Design package is to bring together the right personnel to ensure proper constructability. Our approach is also to ensure that the Project Manager is the central hub for effective communication.

The design is developed to an appropriate level of detail by each DOR. The final documents will be certified by the Designers of Record. They will also be checked by Construction QC managers for contract compliance.

Some projects can be complex, some requiring transition space and a multi- phased, multi- disciplinary repair/ renewal construction approach. Therefore, the design documents need to be detailed enough to describe exactly how Miami Wiipica plans to execute the project. To ensure this is the case, our design typically include the following information:

- Executive Summary – a basic, narrative summary of the Task Order and Scope

- Table of Contents – an outline of the contents of the Work Plan

- Scope of Work – a complete copy of the most current task order SOW

- Site Investigation Report – a summary of the updated annotated Site Investigation Report

- Narrative – a series of detailed discussions of the work to be performed

- Method of Repair and Renovation – an outline of scheduled work to be performed, including the work definition for each task, a narrative of responsibilities, and the rationale behind work assignments

- Asbestos/Lead Paint Abatement Plan – an action plan for the abatement of hazardous materials.

- Specifications – A complete list of project specifications used to support the design drawings and solicit subcontractor bids will be made part of the design package. Specifications will be adapted from the most current version of the masters UFGS specifications at the time of Task Order award. The master specification will be modified to fit the project to include additional requirements that may not be covered in the guide

specification. Editable specification files will be provided to the government at each required design level.

- Manufacturers Data – a summary of equipment and material catalog cuts and specifications

- Government Furnished Materials (GFM) or Government Furnished Equipment (GFE) – Unique to each task order, the Government may elect to provide GFE/ GFM. This will be clearly identified in the design documents with description of expectations. Condition of equipment and/or materials will be inspected and documented before it is transported from storage area to the work site. Any temporarily removed equipment of material will be protected and stored until such time it can be returned . The condition of the items will be thoroughly inspected prior to removal.

- Drawings/Sketches – All engineering drawings showing layouts, locations, equipment and material will be included in the design. Drawings will be provided in Adobe PDF, Autodesk AutoCad and a set of Standard D/ B size prints with a professional certification seal at each required design level.

- Utility Connections – Information regarding utility connections will be gathered from the three companies and shown on the design drawings as required. At JBA, Terrapin Utility Systems Incorporated (TUSI) will be identified as the owner of water and sewer; and Washington Gas on gas systems. At JBAB, the Washington Suburban Sanitary Commission (WSSC) will be contacted to coordinate water/ sewer distribution. We will provide the owners the opportunity to review plans and schedule interconnection.

- Environmental/ Energy Management Control System (EMCS) – All design will include consideration for interconnection into the existing EMCS.

- Security/ Vindicator Tie-ins – If a task order requires installation of a vindicator or other security alarm system, we will coordinate with the base Security Forces at the design stage to ensure it is compatible with the existing base network.

- Design Analysis – a narrative analysis of the final design/layout, to include all assumptions and documentation associated with the “Leadership in Energy and Environmental Design” (LEED®) implementation requirements if required. This will include a color board which is a visual presentation consisting of samples of the various finishes, grouped together based on location within the project that may be required.

- Sustainment Management System (SMS) Builder Data – This is data relevant to the project scope that will enable trained building inspectors, engineers, technicians and maintenance shop personnel to decide when, where and how to best maintain facility infostructure.

- Project Schedule – a schedule completed in accordance with Contract requirements

- Submittal Register – a list of items that must be submitted to the Government

- Site Specific Accident Prevention Plan – an APP with site specific requirements

- Project Specific Quality Control Plan – QC plan with site specific requirements

- Operation and Maintenance Manual Outline – information regarding the type of equipment to be installed in the project, the level of effort and worker requirements for installing and maintaining the equipment. The outline will include a description of the project; description of what was constructed and installed; equipment schedule; pictures of equipment data plates; schematics, diagrams and pictures; catalog cut sheets; manufacturer’s product manuals; list start up procedures, shut downs, user level disassembly/repair; repair procedures; and information necessary to obtain warrant service during the standard 12 month warranty and manufacturer warranty beyond the 12 month period.

- Commissioning Procedure – procedures for startup and testing of equipment & systems

- Training Outline – a proposed outline of training to be provided to facility staff

- Review Comments – a copy of the review comments and any annotations made during the life cycle of the project

Our goal is always to arrive at a design and phasing solution that best minimizes the following:

  - Project Costs

  - Project Duration

  - Transition Costs

  - Movement of Staff Members

  - Disruption to Facility Services

  - Number of Phases

As shown in the flow chart at the beginning of this section, we understand the intricate design, review, comment, approval and development cycle that is typically required by our Government clients.

Design development typically takes between 60 and 120 days, depending upon the size and complexity of the project. This may include Project Definition Design (10% Design), Preliminary Design (30% Design), Intermediate Design (60% Design), Pre-Final Design (90% Design) and Final Design (100% Design) depending on contract requirements. Each of these design stages are followed by Design Charrette followed by charrette reports, Government review periods, comment periods, Design Review Meeting period, document update and submission efforts. Design review meetings will be held within 15 calendar days after responses to government comments and resolved at the meeting as required. Meeting minutes of the design review meeting will be recorded and forwarded to each attendee.

Based on the requirements of the task order, Design Analysis (DA) documents may prepared and submitted for approval at 10%, 25%, 35%, 50%, 65%, 75%, 95% and at 100% design. The DA will include a detailed description of the project requirements and discussion of alternative solutions to technical challenges highlighting advantages and disadvantages. At latter stages of the document, it will include calculations for all structural, electrical, heating, cooling loads, specifics of selected items, other system calculations and recommended Value Engineering measures to improve the performance of the facility. The DA will show the history, assumptions, references, analysis of alternatives, energy conservation analysis/ life cycle cost analysis, and code references as applicable. When major equipment is selected on a project, the DA will include a minimum of 3 manufacturer’s equipment line to fulfill the design requirements.

We understand the importance of having a working partnership with our Government clients to proceed accurately and expeditiously through each of these stages. We also understand the importance of integrating Design Quality Control and coordination efforts throughout each stage.

When the design is nearing completion, the team also begins finalizing the construction schedule, obtaining permits, hiring best-value subcontractors, completing risk analyses and preparing submittals. The submittals requirements will be listed on the submittal register. Miami Wiipica will comply with Attachment 7 Joint Base Andrews Section 01 33 00 Submittal Procedures and the electronic JBAB submittal process that is to be determined at a later date.

These processes allow us to be ready to begin construction immediately upon final design approval by the Government.

The value we add in the Pre-Construction process is our ability to communicate and to ensure proper constructability of the task order documents. We believe the design is the foundation upon which a successful project is constructed. Thus, Our Design and Construction Project Managers work hand-in-hand through this process to create design documents that will allow us to produce success and satisfy the customer.

Customer satisfaction also requires excellent collaboration with our customers. We do all in our power to ensure this collaboration meets the needs of all key partners and stakeholders.

Construction Steps

Once the design is in place and we have obtained approval by the Government, the Design/Build Manager is able to move the project into the Construction Phase.

We include a member of the construction team in every step of the design process, therefore; there are minimal hurdles transitioning from design to construction . In a typical project, our Project Manager will be at work to address constructability issues from the beginning of design. This process allows many of the central project risks to be identified and eliminated or mitigated before construction begins.

Just as our construction teams have a hand in the design process, the entire design team remains assigned to the project and available as needed throughout the project. Their involvement means that any unforeseen site conditions or user-requested changes can be addressed quickly and with the utmost level of project knowledge and history.

We understand that construction cannot begin until formal NTP is provided by the Contracting Officer. Once this is granted, Miami Wiipica initiates construction processes that have been refined during multiple of projects. Our construction teams begin work on the project by holding a series of project kick-off meetings with the end user, base civil engineer, contracting, base support agencies, internal resources and subcontract resources. The purpose of this meeting is to discuss overall project scope, introduce key stakeholders, identify roles and responsibilities, and establish way-ahead to get project started.

The purpose of these meetings is to establish a clear understanding of the following contract requirements:

- Scope Management and Reporting

- Schedule Management and Reporting

- Cost Management and Reporting

- Risk Management and Reporting

- Quality Standards and Methods

- Staffing Obligations

- Safety Requirements

- Infection Control Requirements

- Interim Life Safety Measures

- Facility Rules and Regulations

- Installation Rules and Regulations

- Work Location and Workhours Requirements

- Security Rules and Regulations

- Document Security Requirements

- Closeout Requirements

These kickoff meetings ensure that all key stakeholders are aligned and on-board with the project vision and scope. Work at airfield, controlled area and/or restricted area will include ramp freezes as required. Certain airfield work may have to be completed after flying operations in the evening or on weekends.

Airfield requirements will be addressed at the kickoff meeting provided it is applicable to the project requirement. This applies to work within the secure area of the airfield. We will operate uwthin a radio controlled movement area on the airfield. We will attend the appropriate training on airfield driving safety, escort requirement, crossings at operational runways, construction

equipment requirements, temporary construction waivers and Federal Aviation Administration waiver requirements.

Storage yard and temporary facilities will be discussed at the kickoff meetings. The discussion will establish locations for storage yard, fencing requirements, emergency service access to storage yard, Foreign Object Debris removal requirement, office trailer requirements and utilities for office trailer. All temporary storage yards and temporary facilities will be restored to its original condition within 30 days of contract completion.

When construction begins there are many technical requirements and activities performed by our construction teams. We have found that the best approach to meeting project requirements is to work well with our project partners and stakeholders. This, combined with following the designs, specifications, contract terms and conditions, and our project plan, leads to a successful project.

Following is an outline of some of the actions we would typically take during the construction phase:

- Pre-construction Submittals – Ensure all of the submittals, such as Certificates of Insurance, Surety Bonds, the submittal register, a schedule of values, the construction progress schedule, the infection Control Risk Assessment (ICRA), the Interim Life Safety Measures (ILSM), the Accident Prevention Plan (APP), the Health and Safety Plan, the Environmental Protection Plan (EPP), the Design Documents, the Construction Quality Control Plan, a traffic control plan (if required) and necessary permits are approved. Professionally certified life safety plans, fire suppression/ alarm plans and pre-engineered structures will also be submitted for approval. A TBD web based application will be used for all submittals and shall comply with the JBA Section 01 33 00 Submittal Procedures. Specific instructions for JBAB is TBD.

- Mobilization – While the above activities are taking place, our field personnel begin mobilizing to the site and establishing a temporary project office. They do so by getting the right staffing in place and setting up construction trailers, utilities, signage, and site- specific safety measures according to the approved site plan

until no longer needed. Work within the secure area of the airfield, will require an FAA Form 7460-1 along with Temporary Construction Waiver to be obtained prior to start of construction. The FAA Form 7460-1 will be submitted no less than 45 days prior to the start of construction to the COR.

- Staffing – As the project begins, our Project Manager ensures all subcontractors and tradesmen employ appropriately security cleared manpower with capabilities to perform the functions detailed in the task order.

- Transition Space Setup – Once we are properly mobilized, we will begin setting up the transition space (if required in the Task Order). We ensure the occupants are able to transition to new areas appropriately before we begin inside work.Occupied facilities will be equipped with temporary heating or cooling if the air conditioning system or heating system requires to be shut down to perform the work. Any requirement to shut down heating or cooling without providing temporary service will go through an approval process through the Contracting Officer atleast 15 workdays prior to the interruption.

- Construction – When we have confirmation of access to the building, we set up interim life safety and occupant protection measures, ensure our routes into and out of the facility are safe for everyone, and then embark on the following activities (many of which are iterative in nature):

  - Supervising/managing construction

  - Gaining approval of submittals

  - Supplying personnel, tools, equipment, transportation, materials and supervision to safely and efficiently perform the work

  - Implementing 3 Phase CQC processes

  - Meeting Safety/Health Requirements according to EM 385-1-1

  - Activity Hazard Analysis (AHA)

  - Protecting the environment

  - Providing/maintaining site security

  - Demolishing old construction and abating hazardous materials

  - Completing construction work

  - Documenting the work

  - Maintaining Red-Line Construction Drawings

  - Recording project correspondence

  - Tracking and reporting progress

  - Updating progress schedules

  - Providing schedule status reports

  - Conducting schedule update meetings

  - Controlling quality

  - Processing paperwork

  - Conducting weekly meetings

  - Partnering with stakeholders

  - Producing LEED® documentation if required

  - Preparing Weekly Risk Reports

  - Interfacing with stakeholders

  - Invoicing for completed work

  - Conducting acceptance / contract closeout processes

Quality management is one of the most important aspects of the Construction Phase. We believe quality is not only related to the final product, it is also related to how well we run the project while meeting the needs of our stakeholders.

Our first and foremost goal is to achieve customer satisfaction. This goal causes our staff members to continually seek out and embrace processes that improve our performance quality. For example, we fully implement Corps of Engineers Three Phase methods of Quality Control Management on every project. And we proactively identify risks using weekly reporting formats. All of these, and other performance quality improvement processes, are fundamental to the way we do business.

The Quality Control Plan that Miami Wiipica has developed incorporates, and is patterned after, the Corps of Engineers Three Phase Quality Control Management System.

Our QC processes begin in the very initial stages of the project lifecycle. They start during the Site Investigation and carry through the Design Development and Construction Phases.

Throughout each of these stages, we provide both corporate level and on-site QC of our work.

The combination of our in-house QC oversight, reviews, and the Government design review processes provide excellent quality control of the designs we produce.

During construction, the primary level of QC occurs on-site and is the responsibility of the Quality Control Manager. If the task order does not require a full-time person for this position, the Site Supervisor takes responsibility for QC functions.

The QC Manager or Site Supervisor is directly responsible for project quality management. He creates the project specific Construction Quality Control (CQC) Plan, which includes information about meetings, submittals, inspection, testing, training, commissioning and other important quality management processes. His primary role is to ensure that all work complies with project design and specification documents.

The QC Manager fulfills this role by implementing the Corps of Engineers Three-Phase Quality Control Management Process. This process involves guiding the project team through a Preparatory Phase, an Initial Phase and a Follow-up phase for every feature of work on a project.

The Preparatory Phase ensures that only approved documents are used for construction, safety issues have been addressed (according to EM 385-1-1), and that the contractor performing the work is prepared to execute according to plans and specifications.

The Initial Phase allows the QC Manager to verify that the current contract documents are being used, check to ensure safety procedures are in place prior to beginning work, agree with subcontractors on the level of quality expected, verify that materials and equipment comply with the specifications, and authorize the work to continue.

The Follow-up Phase provides the QC Manager the opportunity to inspect and test work to determine if it meets contract requirements. The QC manager completes a minimum of three project “site walks” every day to follow-up on workmanship, health, safety, and site cleanliness. He also works hand-in-hand with the Safety Manager to ensure the site is safe for all who enter.

The communication and coordination process never ends, but rather extends throughout the project. We constantly communicate with subcontractors, Government representatives, design staff and others regarding progress and issues that arise during construction. We solve problems on site, at the lowest possible level—we are proactive problem solvers.

We know the best way to solve problems is to use available tools such as weekly coordination meetings, look-ahead schedules, project schedule and budget updates, status reports, QC reports, submittal and RFI processes, and RMS/QCS systems. This is exactly how we would handle the work on every task order awarded as a result of this contract.

Closeout Steps

As the project draws to completion, Miami Wiipica ensures that all contract requirements have been met. Acceptance and closeout planning do not begin at the end of the project. We begin closeout planning as early in the process as possible. Following are some of the major activities we would perform during the contract closeout process:

  - Executing the commissioning and closeout plan

  - Conducting QC inspections

  - Commissioning systems

  - Tracking and resolving punch items

  - Certifying and achieving acceptance of deliverables

  - Providing Beneficial Occupancy

sections) & electronic copies at least 7 working days prior to conducting training sessions.

  - Providing appropriate training – On task orders where new equipment has been installed, training will be scheduled and provided for the benefit of Government employees. Manufacturer Authorized training sufficient for JBA and JBAB users to obtain certification in the operation, care, maintenance, and/or repair of the installed systems will be provided that it is offered by the manufacturer. Training documents to include agenda, schedules, training outlines, manuals, videos will be submitted to the Contracting Officer for approval in electronic format at least 15 working days in advance of the training event. Following the completion of the training, class rosters of those who attended will be submitted electronically to the Contracting Officer.

  - Preparing and submitting warranty documentation – A warranty letter that describes that the work performed under the contract conforms to contract requirements and that it is free of any defect in equipment, material, workmanship will be prepared and submitted. This warranty will continue for a period of 1 year from the date of final acceptance of the work or partial beneficial occupancy. Response to warranty calls will take place within 4 hours for emergencies and withing 3 working days for routine calls.

  - Preparing and submitting final record drawings (as-builts) – This is the revised drawings showing the project as built by Miami Wiipica. The revisions from markups and field inspection notes will be transferred to the final as-built set of drawings. This will include modifications during construction, field requested changes, shop drawing modifications and contractor designs. The as-built drawings will also indicate location of all subsurface utility lines. Concurrent with the request for pre-final inspection, a sealed and signed set of as-built drawings will be submitted on AF Form 3000 for Government approval. Once approved, a set of as-built will be submitted in accordance with JBA Section 01 33 00 Submittal Procedures and TBD specific instructions for JBAB. An electronic copy of the site layout and site utility plan will be submitted in ESRI’s GIS shapefile format if required by the task order.

  - Conducting a final facility cleanup

  - Closing out the contract

  - Preparing Form DD1354 documentation 30 days prior to the scheduled Beneficial Occupancy Date.

  - Provide Sustainment Management System (SMS) Builder Data

  - Turning over operations and maintenance of the building to Facility Management

  - Preparing project lessons learned

  - Conducting a Pre-Warranty conference and responding to warranty issues

We understand that how we finish the project impacts the final impression stakeholders have of our company. Thus, the closeout process is critical to our success. We do all in our power to make the closeout process as seamless as possible for our Government stakeholders. Our goal in everything we do is to satisfy our customers, earn their respect and win follow-on task orders.

Conclusion

The approach described in this section has been refined through the successful execution of multiple task order projects. Also, we plan to continue refining our processes as we tailor them to meet the specific requirements of this contract.

# ORGANIZATION ABILITY TO MANAGE MULTIPLE PROJECT

Our management background and structure are founded upon and completely focused on delivering successful construction projects for the Federal Government. We have successfully managed and delivered these projects in multiple facilities throughout the nation.

Furthermore, our design/build construction management background is solid, and we are ready to respond to task orders that result from this contract.

Our team brings significant value and experience to bear on every project. Our customers have applauded us for our culture of being proactive problem solvers. We consistently solve problems at the lowest levels possible, produce quality products, communicate clearly with stakeholders and improve our processes. This culture allows us to provide high performance and customer satisfaction at the lowest cost possible.

To effectively accomplish the objectives of the Program, Miami Wiipica is proud to present our team of dedicated, experienced professionals that have the best processes, behaviors and tools to provide you with outstanding end results.

The team members are supported by additional professionals nationwide who are available to assist and provide specialized support as needed. The members of our team share the mind-set of proactive collaboration; we believe the best projects result when owners, designers, planners and constructors share information and ideas. The team presented below has collaborated on numerous projects together and knows the importance of working together

Miami Wiipica, LLC singular focus is to provide services to our nation's aging federal facilities through design/build renovation, repair and related construction services. Since its inception, it has established a national reputation for construction. To ensure our project delivery is on the mark, each member of our design and construction management team has years of experience in facility design and construction. In keeping with our unified approach to design and construction, most of our designers and managers receive cross-training in multiple disciplines. We deliver service through an interactive approach

– a system in which clients participate as part of the renovation team.

Design Build Consortium, LLC (DBC|KSA) is our team Architect/ Designer should the project require substantial design services. DBC|KSA is a Services Disabled Veteran Owned and Operated Small Business (SDVOSB) that has been focused on supporting federal agencies for various design requirements since 2013.

Local Subcontractors are key members of our Team. We consider local subcontractors who have successfully performed work on the numerous projects as members of our team. We know that our success depends on these skilled crafts people. Therefore, we have nurtured a relationship of hard work, cooperation and respect with our subcontractors.

# Elements of Successful Projects

Effective Management

Both our management background and structure are literally founded upon and completely focused on delivering successful construction projects for the Federal Government. We have successfully managed and delivered these projects in multiple facilities throughout the nation.

Furthermore, our design/build construction management background is solid, and we are ready to respond to task orders that result from this contract.

Conclusion: Our team brings significant value and experience to bear on every project. Additionally, our customers have applauded us for our culture of being proactive problem solvers. We consistently solve problems at the lowest levels possible, produce quality products, communicate clearly with stakeholders and improve our processes. This culture allows us to provide high performance and customer satisfaction at the lowest cost possible.

Experience with Federal Projects (IDIQ)

Indefinite delivery/indefinite quantity (IDIQ) contracts provide government agencies with flexibility, streamlined contracting and faster service delivery. We have a proven record of managing government wide IDIQ and negotiated contracts, which has produced a large portfolio of successful IDIQ task orders.

The bottom line is that we have the depth, breath, and expertise to successfully deliver IDIQ task orders.

Safety: Safe jobs are good jobs

At Miami Wiipica, we understand that accidents are prevented through careful planning, training and cooperative efforts in all areas of our operations. We are committed to safety and believe it is the responsibility of every employee and the project team to make it our focus. We successfully identify and apply effective preventive measures. Safety efforts, while performing construction work within an operating facility, must first focus on maintaining containment of the construction area. They must ensure proper negative pressure of the construction areas and provide proper Infection Control and Interim Life Safety Measures (ILSM).

We place Project Managers and Superintendents on each of our projects with the responsibility to maintain a safe and healthy environment for our team and others affected by our construction.

Collaboration:

Our team embraces projects that enable us to work in partnership with the owner, design team and other stakeholders. Our extensive design-build expertise means less risk and increased certainty for our clients. Through our team’s prior collaboration on many Design-Build projects, we are able to utilize the best design standards, most recent building codes, implement sustainability, ensure client goals and objectives are met, and provide a safe project, within budget and on time.

Quality Control/Quality Assurance:

Quality of work involves aesthetics, creative and innovative solutions, system and facility functionality and effective project and construction management controls. All of our Quality Control (QC) efforts work to meet or exceed the project requirements and the needs of customers.

We are dedicated to having a Quality Manager to oversee the quality control program. Our QC Manager works with job site personnel, subcontractors, the design team and the client to ensure that all work is in complete conformance with the plans and specifications. We understand that a quality project includes:

- Exceeding client quality expectations

- Ensuring a quality project experience for all stakeholders

- Establishing, maintaining and optimizing the project-specific quality control plan

- Ensuring proper quality of project deliverables

- Managing and coordinating testing and inspection programs

- Managing and coordinating project transition, close-out, commissioning and punch list programs

# SCHEDULING METHODOLOGY

Scheduling and Coordination – We employ Project Scheduling software to maintain individual work order schedules. Once Notice to Proceed has been issued for any given work order, the preliminary schedule for that work order is entered into our master schedule log for the contract.

Work tasks are broken down according to which functions will be subcontracted and which will be performed in-house. Subcontractors are advised of work order schedules and are required to adhere to them. They are expected to rapidly execute the work without compromising the integrity of the completion requirements. Project schedules include:

- Subcontractor/in-house task assignments

- Critical Path Method for project continuity and fluid movement of labor and materials

- Inspection dates

- Project milestones

- Material and work unit breakdowns

Subcontractors are informed of project schedules during subcontractor pre-construction meetings. Prior to commencement of work, all scheduling conflicts are identified, and a work order schedule is finalized to accommodate subcontractors, in-house crews, and Government requirements.

Site Supervision – our Project Manager continually monitors Subcontractor work for progress, quality, and safety. Our Project Manager ensures that the project is being constructed according to subcontract agreement and project specifications. Our Quality Control Manager ensures adherence to all facets of the quality control and safety plans. Our Project Manager administers each subcontract agreement, conducts spot inspections, and accompanies contracting personnel on work-in-progress site visits.

# PLAN FOR PROVIDING ADDITIONAL RESOURCES MANPOWER

Subcontractor selection is task order driven. Our subcontractor pool is already well established. Upon receipt of Request for Proposals from the Government, we use the following procedures for subcontractor selection:

- Evaluate task requirement

- Evaluate subcontractor’s expertise, performance history, current workload, and ability to properly staff the project

- Schedule site visit for Specialty Subcontractor

- Discuss project requirements and timetable for execution

- Distribute scope of work, plans, and specifications

- Receive subcontractor quotes

- Discuss cost factors and ability to meet project requirements and schedules

- Identify successful bidder

- Execute subcontract agreement, upon submittal approval and Notice to Proceed

- Initiate project execution according to schedule

Final subcontractor selection is based primarily on the requirements of the task order. Price, reliability and technical expertise are always considered. The following factors are routinely considered in our final source selection:

  - Subcontractor’s competence, integrity, professionalism, and financial capability based on historic experience, reliable references, and direct interviews

  - Reasonable pricing consistent with project budget and requirements

  - Subcontractor’s understanding of the scope

  - Ability to perform work as scheduled, and according to the Government’s needs

  - Available capacity and market conditions

# Subcontractor Management

A comprehensive subcontractor selection plan lays the groundwork for quality subcontractor management. Thorough research enables us to obtain high quality, reputable, adequately capitalized subcontractors. Risk of conflicts and work deficiencies decrease, while efficiency increases. Our approach to subcontractor management is outlined as follows:

Preconstruction coordination emphasizing the following points:

- Formally executed subcontract agreement

- Verified subcontractor insurance and worker’s compensation

- Inclusive review of subcontractor agreement, i.e. Davis-Bacon wage rates, certified payroll requirements, quality control, and safety criteria

- Completed Statement and Acknowledgment form

- Project requirements

- Project schedules

- Lines of authority

- Quality control and Quality Control Manager’s authority to direct work correction

- Safety plan, accident reporting, and emergency procedures

- Payment and routine contract administration

- Invoicing and the Prompt Payment Act

On-going subcontractor management is dependent upon task order size, complexity, and overall project workload. During project execution the following required procedures ensure effective and efficient subcontractor management:

- Daily contact between Project Manager, Quality Control Manager, and subcontractor’s Superintendent

- Discussion of scheduling and assignment of tasks

- Coordination of simultaneous task orders between subcontractor and in house personnel

- Coordination of security or access to work area

- Subcontractor attendance at quality control and safety meetings

- Subcontractor quality and safety

- Identification of any work deficiencies

- Development of timetable and criteria for correction of deficiencies

- Inspection to verify completion of rework items

- Assessment of subcontractor progress through regular inspection by Quality Control Manager, Superintendent, and Project Manager

- Evaluation of subcontractor progress and notification to subcontractor

- Recommendation by Project Manager of steps needed to rectify unsatisfactory progress

- Verification of implementation of measures to rectify unsatisfactory progress

Dispute Resolution – In the event a dispute arises with a subcontractor, the Project Manager will immediately determine the exact nature of the dispute, the subcontractor’s position, and our corporate position. A meeting is then scheduled to resolve the dispute. We make certain that contracts between our firm and the customer, as well as contracts between our firm and subcontractors, include the necessary guidelines for dispute resolution. We have successfully resolved subcontractor disputes while maintaining critical project schedules. However, we reserve the right to terminate an unreasonable subcontractor or supplier if the project schedule becomes threatened. Our subcontracts provide for mandatory, binding arbitration, which has been shown to be a prompt, effective method for resolving differences.

# Subcontractor Response

Subcontractor performance is constantly monitored by our on-site project management team and noted in our Subcontractor Performance Log. Subcontractors are evaluated using the same criteria as that used during the selection process. We review evaluations with each subcontractor and make recommendations to improve deficiencies.

Quick Response Capability – Our subcontractors have prior experience in the task orders/negotiated contracting environment. Our subcontractors understand that quick response and speedy construction is the cornerstone of contracting. We believe that contractor performance according to Government requirements will result in quality constructed projects delivered on time, in time, and in a safety conscious environment.

Understanding the need for quick response is important. But proper, timely execution is critical for project delivery to be beneficial to the Government. Our Quick Response Capability ensures that the following parameters continually exist on-site:

- Our subcontractors are required to estimate as quickly as we do

- Our on-site professional staff is comprised of skilled estimators capable of developing large volumes of unit price proposals in a short amount of time

- Our project management personnel are experienced in motivating and training subcontractors in the concept and operations of task orders

- We and our subcontractors are motivated to deserve the Government’s maximum possible workload by providing Quick Response to Government needs

- The performance-based nature of task orders demands accurate, efficient production in every phase of work order development and execution

- In our support of our subcontracted effort, and to further enhance our Quick Response Capability, we maintain a skilled in-house workforce, able to provide immediate response to urgent and emergency requirements in every division of construction

# SUFFICIENT QUANTITY OF QUALIFIED PERSONNEL

Employee retention and job satisfaction is high on Miami Wiipica priorities. Our managers take on the responsibility of managing effective retention strategies to decrease turnover. Some of the key strategies practiced at our organization include orientation, compensation, communication/ feedback, annual reviews, training, recognition/ reward system and acknowledging milestones.

Every new hire will be set up for success from the very start. New staff members will be introduced not only about the job but also the company culture and how they can contribute and thrive.

Attractive and competitive compensation packages are provided. That includes salaries, bonuses, paid time off, health benefits and retirement plans. Every employee is briefed on all benefits from the beginning.

We maintain an open line of communication with upper management so employees feel they can discuss ideas, questions and concerns, and they expect you to be honest and open with them about improvements they need to make in their performance. During the annual reviews, we discuss short- and long-term goals and talk about their future with the company. We discuss potential advancement scenarios and try to map out a path.

We consider professional development and finding ways employees will grow a win-win. We encourage our workers to attend some conferences or industry events each year, provide tuition reimbursement, or pay for continuing education training relevant for their position in the company.

Every person wants to feel appreciated for the work they do. Therefore, we make it a habit to thank all employees that go the extra mile with a sincere email, a gift card or an extra day off. Whether the team just finished a huge project under budget, or an employee celebrated a work anniversary, we celebrate together with a shared meal or a recognition gift.

# Hiring Criteria - Key Positions

The hiring criteria shown in the matrix below varies based on the various positions that may be required to execute the projects resulting from the contract.

| Positions | Qualifications |
| --- | --- |
| Program Manager | - Engineering or construction degree plus 10 years of management experience or 15 years of experience in construction management |

| Positions | Qualifications |
| --- | --- |
|  | - Familiar with government contracting process - Maintain open line of communication - Skilled in line item estimating and negotiation - Able to recruit, hire, train, and manage personnel - Experienced in scheduling and subcontractor management - Computer literate - Excellent communication skills - Team player |
| Project Manager | - Engineering or construction degree plus 5 years of management experience or 10 years construction management experience - Familiar with government contracting process - Maintain open line of communication - Skilled in line item estimating and negotiation - Able to recruit, hire, train, and manage personnel - Experienced in scheduling and subcontractor management - Computer literate - Construction Quality Management certified - OSHA certified - Knowledge of building codes and requirements - Excellent communication skills - Able to manage multiple projects - Team player - Knowledge of financial process |
| Site Superintendent | - Engineering or construction degree plus 5 years of general construction experience or 10 years of general construction experience - Familiar with government contracting process - Maintain open line of communication - Skilled in line item estimating and negotiation - Able to supervise multiple subcontractors & multiple tasks - Experienced in scheduling and subcontractor management - Knowledge of Word, Excel, and scheduling software - Team player - Effective communicator - OSHA certified - Construction Quality Management certified |
| QC Manager | - Engineering or construction degree plus 5 years of general construction experience or 10 years general construction experience - Familiar with government contracting process - Maintain open line of communication - Construction Quality Management certified - OSHA certified - Knowledge of building codes and requirements |

| Positions | Qualifications |
| --- | --- |
|  | - Excellent communication skills - Able to manage multiple projects - Team player |
| QC Inspector | - Engineering or construction degree plus 5 years of construction experience or 10 years of multi-trades construction experience - Familiar with government contracting process - Maintain open line of communication - Able to recruit, hire and train personnel - Computer literate - Construction Quality Management certified - OSHA certified - Knowledge of building codes and requirements - Excellent communication skills - Able to manage multiple projects - Team player |
| Office Manager | - 5 years of construction office management experience - Knowledge of accounting and bookkeeping practices - General clerical and computer skills |
| Project Designer | - PE license or registered architect (AIA) and 5 years of experience - Knowledge of building codes and requirements - Excellent communication skills - Able to manage multiple projects - Team player - Able to recruit, hire, and train personnel |
| CADD | - 3 years CADD experience - Able to manage multiple projects - Team player |

# EVALUATING AND SELECTING ARCHITECT / ENGINEERING (A/E) FIRM ON D/B TASK ORDERS

Our Project Managers work hand-in-hand with our Design Manager to integrate our design teams with construction professionals. Together, these managers have the authority to make design decisions. This integration is the most important aspect of our ability to solve design   problems and perform at high levels as a Design-Build construction firm.

During all of our Design-Build projects, our team works together to understand and integrate the owner’s requests and expectations while staying within the contract cost limitations.

As our team members review the drawings and make comments, we are able to integrate innovative thoughts and ideas into the project. This integration effort has produced huge dividends for our customers, as we are able to meet their requirements in both cost-effective and innovative ways.

This review and integration process has also provided a mechanism for us to control project risks. As we engage in open, transparent communication regarding project requirements and potential solutions with our customers and our team members, we are better able to control common Design-Build risks such as scope creep, cost growth, schedule impacts, resourcing issues and other problems that arise in a fluid Design-Build scenario.

In the selection of Design Manager while we give special consideration to the use of small, disadvantaged and minority subcontractors, we will not compromise our safety, quality, and experience standards. Under ordinary circumstances, we prefer to solicit (3) bids and review cost factors and subcontractor availability prior to awarding task orders. However, when emergency or urgent circumstances dictate, subcontractor selection is based on qualifications, past cost history, and ability to provide immediate response.