## Est FINAL 0929
CONSTRUCTION COST ESTIMATE BREAKDOWN
CONTRACTOR |  | ADDRESS |  |  | ISSUED BY/OWNER:
Toole Corp |  |  |  |  | HOMESTEAD AIR FORCE RESERVE BASE |  |  |  |  | 29050 CORAL SEA BLVD, HOMESTEAD, FL 33039
RE: |  |  | ESTIMATE DATE |  |  |  |  | PROPOSED TOTAL CONTRACT PRICE
Repair Stairwell Bldg 410 |  |  | 2012-09-22 | [8 empty] | 308023.9123
SOLICITATION/PURCHASE REQUEST NUMBER |  |  |  |  | PROJECT NUMBER |  |  | WORK LOCATION
[5 empty] | KYJM 11-9032 |  |  | HOMESTEAD AIR FORCE RESERVE BASE
[7 empty] | MATERIAL COST |  | LABOR COST
LINE NO. | ITEM |  |  |  | UNIT OF MEASURE | QTY | UNIT | TOTAL | AVERAGE RATE | TOTAL | OTHER DIR COST | LINE TOTAL
Building 410
1 | Mobilization and General Expenses |  |  |  | LS | 1 | 2200 | 2200 | 3870 | 3870 |  | 6070
2 | Dumpster and Dump Fees, 30 CY, 1 Dump/ Wk |  |  |  | EA | 3 | 495 | 1485 |  | 0 |  | 1485
3 | On-Site Superintendent (Incl Per Diem) |  |  |  | HR | 640 |  |  | 35 | 22400 |  | 22400
4 | Off-Site Supervisor |  |  |  | HR | 160 |  | 0 | 27 | 4320 |  | 4320
5 | Geotechnical Investigation |  |  |  | JOB | 1 |  | 0 | 0 | 0 | 1400 | 1400
6 | Site work (landing/sidewalk) |  |  |  | JOB | 1 |  | 0 | 0 | 0 | 15000 | 15000
7 | Concrete Landing/Sidewalk (w/ vapor barrier) |  |  |  | CY | 0 | 250 | 0 | 175 | 0 |  | 0
8 | Wall/window demolition |  |  |  | LS | 0 |  | 0 | 0 | 0 | 3250 | 3250
9 | Carpentry (handrails, fixtures, hardware, etc.) |  |  |  | LS | 0 |  | 0 | 0 | 0 | 12000 | 12000
10 | Material storage |  |  |  | JOB | 0 |  |  | 0 | 0 | 1780 | 1780
11 | Relocate electric |  |  |  | LS | 0 |  | 0 | 0.8 | 0 | 6300 | 6300
12 | Misc CMU wall repair |  |  |  | LS | 0 |  | 0 | 0 | 0 | 4750 | 4750
13 | Temporary Cover Protection |  |  |  | LS | 0 |  | 0 | 0 | 0 | 3500 | 3500
14 | CMU Waterproofing |  |  |  | SF | 264 | 2 | 528 | 5 | 1320 | 0 | 1848
15 | Fabricate Stairwell (incl wire fabric panels west stairs) |  |  |  | JOB | 0 |  | 0 |  | 0 | 77240 | 77240
16 | Erect/Install Stairwell (incl wire fabric panels west stairs) |  |  |  | JOB | 0 |  | 0 | 0 | 0 | 6000 | 6000
17 | Paint Stairwells (incl fabric panels on west) |  |  |  | LS | 0 |  | 0 | 0 | 0 | 6000 | 6000
18 | Rubber Wall Base |  |  |  | LF | 275 | 2.2 | 605 | 0.15 | 41.25 | 0 | 646.25
19 | Remove/replace Carpet |  |  |  | SY | 60 | 38 | 2280 | 28 | 1680 | 0 | 3960
20 | Replace ACT |  |  |  | SF | 1560 | 3.3 | 5148 | 1.2 | 1872 | 0 | 7020
21 | Replace Drywall |  |  |  | SF | 420 | 1.75 | 735 | 2.75 | 1155 | 0 | 1890
22 | Texture Walls |  |  |  | SF | 420 | 0.65 | 273 | 1.45 | 609 | 0 | 882
23 | Paint Walls |  |  |  | SF | 2700 | 0.4 | 1080 | 0.85 | 2295 | 0 | 3375
24 | Install Vannity Fixtures (only) |  |  |  | EA | 37 | 250 | 9250 | 145 | 5365 | 0 | 14615
25 | Extra Vannity Fixtures |  |  |  | EA | 7 | 250 | 1750 | 0 | 0 | 0 | 1750
26 | Install Emergency Access Doors (incl hardware) |  |  |  | EA | 2 | 1350 | 2700 | 1500 | 3000 |  | 5700
27 | Electrical Matl + Install (pull stations, mass notification, emerg lights) |  |  |  | JOB | 1 |  | 0 | 0 | 0 | 16258 | 16258
28 | Repair SOD |  |  |  | LS | 1 |  | 0 | 0 | 0 | 4200 | 4200 |  | 164226
29 | Project Manager |  |  |  | Days | 7 |  | 0 | 951 | 6657 |  | 6657 |  | 147803
30 | Architect (Construction phase) |  |  |  | Days | 15 |  | 0 | 555 | 8325 |  | 8325 |  | 16423
31 | MEP Engineer (Construction phase) |  |  |  | Days | 10 |  | 0 | 600 | 6000 |  | 6000 |  | 8211.5
32 | MEP Expenses |  |  |  | JOB | 1 |  | 0 | 0 | 0 | 6548 | 6548
| GRAND SUBTOTAL | [6 empty] | 29482 |  | 67459 | 156014.5 | 252955.5 |  | 266269.25
[10 empty] | Overhead | 10.7% | 27066.2385 |  | 28539.26
[8 empty] | 29482 |  | Subtotal |  | 280021.7385 |  | 294808.51
[10 empty] | Profit | 10% | 28002.1738 |  | 44221.2765
[10 empty] | Grand Total |  | 308023.9123 |  | 339029.7865
[10 empty] | A/E | 6% | 18481.4347 | 19983 | 1501.5653
326505.3471
[10 empty] | Bonding | 2.5% | 8162.6337
334667.9808