Gannt Chart Narrative

Project Award

- Assuming a 10/1/19 Project Award per the specifications.

File FAA 7460/Waiting Period

- Upon award Tavares will submit the FAA 7460 form as instructed on the construction documents with an anticipated approval waiting period of 45-60 days. The maximum of 60 days was carried in the attached schedule.

Submittals

- Submittal process will begin upon project award and per the specifications.

Construction Start/Mobilization

- The following items will be utilized during mobilization on site.

  - Temp fencing

  - Erosion Control as indicated on the construction drawings

  - Trailer to be located on site within the parking area.

  - Generator to be located near the trailer to provide power on a daily basis. Demolition lighting will be provided by a separate generator.

  - Red indicator lights at corners of the property per construction document instructions, utilizing (2) boom lifts with ground controls.

Traditional Abatement

- Removal and disposal of ACM and OHM/Regulated wastes as specified in the Asbestos Abatement Section 02 82 13.00, Removal and Disposal of PCBS Specification Section 02 84 33, and Hazardous Building Materials Inspection Report by Cardno ATC Dated March 8th, 2013.

- Removal of the basement water to be treated offsite as ACM.

- Removal of the exterior building envelope as indicated as ACM utilizing (2) machines to carefully break apart the ACM materials

Non-Traditional Abatement

- Includes removal and disposal of Black Coating on Structural Steel, Black Coating on Concrete Encased Columns, CMU Block, and Brick Façade as ACM under a NTWP (Non-Traditional Work Plan) provided by Tavares. It is assumed the entirety of the Black Coating can be removed under this item under the NTWP without conventional abatement. Scope also includes removal and disposal of PCB Caulking as referenced in Limited PCB Sealant Survey Dated January 25th, 2012 under the NTWP with the ACM. It is assumed that Black Coating is only on the exterior structural members of the building.

Water Removal

- Includes removal and disposal of water in basement as asbestos containing water to be hauled & disposed off-site. Quantity is limited to 60,000 Gallons.

Site Utilities Cut/Cap

- Activity includes removal of site utilities and asphalt in accordance with Utility Demolition Plan C1 and Site Demolition Plan C1. Also include is the cutting and capping of (1) Water Service Line, (1) Sewer Line, and (1) Drain Line.

Steel and Concrete Demolition

- The complete demolition and removal of Building 1103. Included is the removal of the slab on grade and below grade foundation walls. Removal of any deep foundation elements (e.g. piles, caissons, etc.) is excluded (if applicable).

Asphalt Removal

- Removal of asphalt to be completed post building demolition so allow the trucks and machines access while reducing the amount debris tracked throughout the site.

Transformer Removal

- Includes removal and disposal of transformer located within the building basement. Pricing assumes the transformer contains PCBs.

Backfill/Grading/loam/seed/site finishes

- Backfill existing foundation area to existing surrounding grade with gravel borrow per specifications and tested by Tavares Geotech Consultant, installation of curbing and sidewalk, repair of asphalt, and loam and seed disturbed areas in accordance with Site Restoration Plan C1.

Demobilization/Closeout

- During this period the Tavares will utilize their remaining time on site to finalize documentation per the specifications and construction documents.

- Remove Temp Fencing and trailers.