2.2 Area of Consideration 1 – Seed Project

2.2a Line Item Breakdown:

See Attachment #1 – Attachment 6 Breakdown

2.2b Rationale

| Description | Rationale |
| --- | --- |
| Site protection | As part of environmental protection requirements, the surrounding site must be secured prior to excavation |
| Excavation | In order to properly install the sona tub concrete pour underground the site must first be excavated |
| SonoTube Form | In order to ensure consistency with existing sizes/dimensions of the existing concrete forms a sonotube will be used |
| Concrete | Necessary for mounting light pole – must satisfy all applicable PSI requirements |
| Light poles | Elevation established by SOW requirements |
| Solar Panel | Part of the requirement to charge batteries – placement field determined |
| LED lighting | Necessary to achieve lumens as per chart |

2.2c Non Pre-priced Items:

Hazardous material testing – depends on the type of materials that are uncovered

Hazardous material removal – in order to price you need to know the quantity of material to be removed and disposed.

2.2d Period of performance

75 days

When you read [sow #.#] it reference the 99th Readiness Division Scope of Work and the paragraph number as per D2.4 instructions.

2.4

Tavares Team of Principals, Management, and Employees have extensive experience in working in varying Construction Environments in the 99th Readiness Division Area of Responsibility Region A as evidenced by our numerous projects throughout the New England Area.

Our team is acutely aware of the conditions that affect construction, maintenance, and repair projects in both warm and cold climates. Conditions can vary from summer to winter, state to state, and busy to slow season. Being cognizant of the various micro and macro environments throughout this region allows the Tavares Team the ability to be flexible and immediate in our response to our clients’ needs. Our employees have worked on several Construction projects at facilities throughout Northeast over the past 10 years, the below list of projects are but just a few worth mentioning:

Foxwoods Millwork Install 				Ledyard, CT

211 South Main Street				Middletown, CT

Easton Building National Park Service		Boston, MA

Wynn Boston Harbor					Everett, MA

Stacy’s Pita Chip					Randolph, MA

Roger Williams University 				Bristol, RI

Providence Innovation Center 			Providence, RI

Anheuser-Busch					Merri Mack, NH

Our employee’s work at the Easton Building best demonstrate our awareness to of working for a federal client, Department of the Interior in a fully occupied building.

The work involved Renovation of the National Park Service, Northeast Region Headquarters, Easton Building, 15 State Street, Boston, MA. Work includes renovation of the first and second floors, including the Base Work: (a) Removal of existing stairs from 2nd floor entrance lobby and structural infill of the opening between the first and second floors; (b) Renovation of the main second floor entrance lobby with new stair and landing, an inclined stair lift, new separation partitions with doors and glazed openings; (c) Renovation of second floor service spaces, including new restrooms, pantry and storage room; and renovation of first floor service entrance ramp to meet accessibility standards.

Where there are specific conditions that must be adhered to, such as furnishing all submittals, handling of subcontractors, institution of a quality control plan and working in a fully occupied space, the Tavares Team has extensive experience and quality required to work in a federal facility environment, the Tavares Team has extensive experience and quality required to work in a federal facility environment.

Tavares Corporate Office is located in Providence Rhode Island with an office location in Salem, New Hampshire.  Tavares key management personnel, Mr. Fernando Tavares, Owner, Mr. Jack Kowal, Project Superintendent, Mr. Brian Labonte, Project Manager, Chris Ferrant, Sr. Project Manager, Gabriel Francisco, Quality Control Manager, Paula Lisa, Assistant Program Manager, have successfully performed projects on contracts with the Department of Interior, National Parks, United States Coast Guard, Hanscom AFB, Newport Naval and civilian agencies such as Gilbane Building Company,  Harvard University, Massachusetts Port Authority, Suffolk Construction Co., Whiting-Turner, Northeastern University.

See Resumes – Exhibit 4

Our Team has managed teams of multi-discipline subcontractors, small and large businesses which enable us to extend our professional arm all over the world, at the drop of a dime. We have the necessary skill sets and experiences to program manage and administer the 99th Division Readiness Region A contract and associated task orders within compliance.

SITE DESCRIPTION

The work is to be done at Conneaut Lake, PA which consists of installing 4 new solar parking lot light poles off grid. The new 25’ solar light poles will have solar panels mounted on the top to increase the charging capability of the off grid solar light poles to batteries.

It is our understanding that 99th DIV would like the poles installed at the locations identified on the drawing based on the shading of existing trees and position of the Sun. The depth and circumference of the solar light pole holes and the PSI strength of concrete used will be per the specifications of the Inovus type lights or equivalent. The sonotube concrete pour sizes/dimensions shall match the existing solar light polls that already exist and be high enough to protect the solar light poles from vehicle damage.

[sow 1.6] Contractor can only work on permitted days during acceptable hours of operation as per the contract requirements.

PROJECT ORGANIZATION

The Contractor’s key personnel assigned to this project should possess a broad range of construction experience and skills. All should have experience working on federal sites and should be familiar with the requirements of day-to-day work under this specific contract.

The functional responsibilities of key technical personnel are summarized as follows.

Contractor – Project Executive

The Contractor’s Project Executive will ultimately be responsible for the project's success. He will provide the required resources to ensure that the project is successfully executed. He will be kept informed of the project's progress and maintain that the project is meeting its goals. The President will also serve as the acting Project Manager and will resolve problems that cannot be resolved by the On-site Construction Superintendent or Quality Control Manager.

FIELD PERSONNEL

The Contractor’s field personnel should rely on home office support throughout the course of the project. The Contractor’s Construction Superintendent will become and remain personally involved until each problem is resolved and appropriate corrective measures are implemented. He will typically communicate at least once daily on the progress of the project. The Project Manager will visit the jobsite as needed periodically to ensure that the project is progressing as scheduled.

[sow 2.2] The Construction Superintendent is responsible for implementation and support of the Contractor’s Construction Quality Control Plan (CQCP) and will oversee all aspects of work under this contract for remediation at the site, including:

- All procurements.

- Qualified Contractor and subcontractor resources are assigned to the project and balanced to ensure jobs are aligned with project needs.

- The Site is maintained and secure.

- All tasks are carried out safely and in compliance with the project specifications.

His responsibilities include:

- Contractor coordination.

- Acting as site liaison between the Contractor and 99TH READINESS DIVISON.

- Maintaining charge of all field operations.

- Implement the Quality Control Plan

- Ensure compliance with the Site Safety Plan

Contractor - Quality Representative (QR)

For the purposes of the JOC seed project the Construction superintendent will double as the Quality Representative. He will have both the authority and the duty to halt any operation appearing to be out of compliance with contract specifications.

The QR is responsible for keeping and maintaining all records related to personnel, supplies, equipment use, and equipment calibration and sampling. His function will be to ensure compliance with the contract plans and specifications.

QR responsibilities include:

- Performing and documenting field inspections.

- Preparing daily Quality Control Reports.

- Scheduling, reviewing, certifying, and managing project submittals.

- Maintaining the Submittal Register.

- Providing coordination of required quality control testing, reviewing results, and submitting.

- Coordinating, documenting, and tracking preparatory, initial, and follow-up inspections.

- Tracking construction deficiencies and ensuring timely corrective action.

- Coordinating field sampling activities (as required).

- Preparing addenda to the CQCP as necessary when additional phases of work are added.

- Maintenance of as-built drawings.

- Coordinating responses to vendors’ requests for information and technical issues.

- Serving as main point of contact at the site for 99TH READINESS DIVISON CO/CE questions and discussions on quality and technical issues.

Depending upon project size Tavares may elect to bring a separate QR to be present on-site when work is being performed.

1. QUALITY CONTROL METHODS

[sow 4.1, 4.2, 4.3] The Construction Quality Control Plan will be implemented in order to ensure compliance with USACE EM 385-1-1, 29 CFR 1910, OSHA, NFPA and all other specifications for construction as detailed in the contract specifications. The basis of the Construction Quality Control Plan is nationally recognized standards published by the American Society for Testing and Materials (ASTM) and the Project Specifications. In addition, procedures utilized within the QCP should reflect the experience gained by Tavares in completing construction projects similar to seed project in performing excavation, site protection, concrete footings and electrical installation.

Quality control measures will extend to field sampling procedures; staffing; types of material and equipment to be used; and methods of performing, documenting, and enforcing quality control operations of both the Contractor and subcontractors (including inspection and testing).

The maintenance of the QCP will be the responsibility of the Construction Superintendent/QR. The QR will be responsible for ensuring that all materials and work comply with the contract specifications.

It is anticipated that the 99TH READINESS DIVISON CO/CE representative and the Contractor’s QR will meet frequently in order to forecast and/or prevent any potential problems from arising.

[sow 3.2.1.5] The QR will record project activities in a daily quality control report maintained on site at all times. All site activities, site inspections, and field testing of materials will be recorded on a daily basis, along with any unacceptable site occurrences or deficiencies and their associated corrective actions. Each daily entry into the report will be signed by the QR. Quality control reports will be submitted on a weekly basis during all field construction activities.

2. INSPECTIONS

To ensure that all construction and excavation activities, subcontractors comply with the project specifications, the QR will complete, in conjunction with the subcontractors, three phases of site inspections for each feature of work. These inspections will include the following:

PHASE I - PREPARATORY INSPECTION

Preparatory inspections will be performed prior to beginning work on any definable feature of the project and will include:

- Review of submittal requirements and all other Contract requirements with the performance of the work;

- Check to assure that provisions have been made to provide required field quality control testing;

- Examine the work area to ascertain that all preliminary work has been completed;

- Verify all field dimensions and advise 99TH READINESS DIVISON CO/CE of any discrepancies;

- Perform a physical examination of materials and equipment to assure that they conform to approved shop drawings or submittal data and that all required materials and/or equipment are on hand and comply with the Contract requirements.

- [sow 1.8] Shall call/coordinate prior to excavation with local municipalities and the facility utilities section to identify all underground utilities.

Subsequent to the preparatory inspection and prior to commencement of work, the Contractor shall instruct each applicable worker on the level of workmanship required to meet contract specifications.

PHASE II - INITIAL INSPECTIONS

Initial phase inspections will be performed as soon as a representative portion of the particular feature of work has been accomplished. Initial inspections include, but are not limited to, examination of the quality of workmanship; review of control testing for compliance with control requirements; and identification of defective or damaged materials, omissions, and dimensional requirements.

The initial phase inspection is the time to discuss and agree on the required level of quality associated with a given work activity. Any discrepancies relative to work quality should be addressed at this time.

[sow 1.8.2] Make sure a copy of the approval notification letter or valid authorization number is available at the time for inspection of the excavation site.

III - FOLLOW-UP INSPECTIONS

Follow-up inspections will be performed daily as work progresses to ensure continuing compliance with contract requirements, including control testing, until completion of the particular feature of work. Final follow-up inspections will be conducted, and deficiencies corrected prior to beginning new work.

The QR will notify 99TH READINESS DIVISON CO/CE at least 24 hours in advance of any inspections. Notification and meeting minutes of all inspections will be recorded in the Daily Quality Control Report. Examples of the inspection forms to be utilized are presented in Appendix B.

3. SUBMITTALS [sow 1.3]

The QR will follow standard procedures concerning submittals, including the use of any assigned transmittal form. Each submittal form may contain more than one submittal specific to that specification section. A submittal register listing major submittals will be prepared. This register will be prepared in conjunction with the anticipated progress schedule.

[sow 10.2]

Original and four (4) copies of each submittal shall be provided and signed by the contractor. Thirty (30) days prior to contract completion date, original and four copies of ALL final documentation: submittals, certifications, laboratory testing, shop drawings, site survey’s, As-builts will be sent to:

99th Readiness Division HQ

Attn: DWP Operations: Contract # _____

Fort Dix, NJ 08640

4. DOCUMENTATION

[sow 1.5] Prior to the start of the project the Project Manager will send a letter appointing the Construction Superintendent for the project.

[sow 1.6.1] Once assigned the Construction Superintendent will send the entry letter for all vehicles including subcontractor vehicles.

[sow 1.4] Tavares may not commence with the project until after receipt of the NTP.

[sow 11.1.5, 11.1.2] Tavares staff and subcontractors will be required to attend and complete AT Level I training and iWATCH training.

Hazardous Material Contact [sow 4.8]

All testing results will be recorded on the daily quality control report. Any concerns or deviations from the required material specifications and the actions taken to correct the problems will be noted on the report. Information recorded on the daily quality control report will include:

- Definable features of work that was addressed.

- Description of trades working on the project.

- Numbers of personnel.

- Weather conditions.

- Nature of defects or cause for rejection.

- Proposed corrective action(s).

- Corrective action taken and date.

- Delays encountered.

- Directions received from the Engineer and actions taken.

- Health and safety issues or deficiencies and how they were resolved.

- Deficiencies.

[sow 4.9] Provide and maintain strict compliance with all federal, state, county and local environmental protection requirements including but not limited to, water, soil, air, and noise pollution.

5. REVISIONS TO WORK

The Contractor will be responsible for ensuring total compliance of field work to the project specifications. Should modifications or revisions to the specifications become necessary, the Contractor will make the request, in writing, to 99TH READINESS DIVISON CO/CE. Approval from 99TH READINESS DIVISON CO/CE must be received prior to allowing the modifications or revisions to be made in the field. The QR will be informed of and record all such requests in his daily log and on the daily quality control report.

6. CORRECTIVE ACTIONS

We bring QC processes and procedures that have been proven effective at detecting and correcting conditions adverse to quality. These processes are networked throughout our contracts and, as they are refined and updated at the local level, are available on a real-time basis to our quality personnel. Components of our QC program include:

- Project designs are reviewed by the customer and field operations to ensure the proposed project will meet performance, safety, maintainability, and other design criteria.

- For example, a design review at one project identified a missing isolation valve in an HVAC design that would have severely compromised the systems performance if it had not been installed.

- All components are inspected upon receipt to ensure that they meet specifications and are not damaged.

- Installations and major repairs are commissioned to ensure systems were installed in accordance with the approved design, that systems perform as specified in the design specification, and that we adhere to baseline operating parameters for maintenance.

At Tavares, we have developed procedures specifically for tracking construction deficiencies from identification, through acceptable corrective action, to verification that identified deficiencies have been corrected. These procedures ensure that we:

- Review each applicable specification. Perform, daily inspections of the work area to ensure all preliminary work has been completed and is in compliance with contract requirements.

- Examine all required materials, and equipment to ensure they conform to approved shop drawings or submitted data, and are properly stored.

- Perform a hazard Analysis to ensure safety requirements are met.

- Verify required control inspection and testing is performed per specifications. Document any construction deficiencies observed.

- Develop a "punch list" of items which do not conform to the approved plans and specifications and document them in our daily Quality Control Inspection Report.

- Provide an estimated time by which the deficiencies will be corrected.

- Correct all deficiencies.

- Perform a follow-up inspection to ascertain that all deficiencies have been corrected.

7. SITE SAFETY PLAN

The Tavares team recognizes that there are many elements which must be brought together in order to achieve an effective safety program. First, there must be a commitment by management to provide the environment, encouragement and support needed to attain excellence in safety performance. Tavares has an EMR of .69 demonstrating our commitment to safety.

Since we expect to work at hazardous sites during the life of the program we will provide the tools necessary to implement the program. Such tools include definition of responsibilities, inspection of jobsites, jobsite meetings, safety rules, safety training, job planning, and accident investigation.

Below is an outline of our typical Project Safety Program. Since projects may have different requirements, or may require additional safety items, the Tavares team will tailor, submit, and the implement project safety programs that best meets the need of the particular project. Each project safety program will be submitted in accordance with OCCUPATIONAL SAFETY AND HEALTH REQUIREMENTS and as directed by the Installation Design Plan.

7.A Steps during construction

Elements of our Project Specific Safety Plans include:

- New Job Start-up and Weekly Safety Program

  - List of first aid supplies and location(s).

  - Required personal protective equipment.

  - Vehicle inspection Checklist.

  - Fire Prevention and Control.

  - Posting of Emergency telephone numbers, Insurance information, maps showing the route to the closest hospital and all required State and Federal posters.

  - Start weekly safety meetings (including all subcontractors).

  - Document chain of command and responsibilities.

  - Hazard Analysis sheets and information.

- Documentation of Job Safety Program

  - General safety practices and procedures.

  - Employee indoctrination

  - Specific job safety practices and procedures.

  - Safe Operating Practices and Procedures (Rules).

  - Job training requirements and programs.

- Specific Documentation

- Accident Reports.

- Accident Investigations.

- Liability Claims.

- Employee Safety Files.

- Month End Accident Reports.

- Job Site Incident Reports.

Steps to Promote Safety

- Supervisor’s Safety Meeting

On many projects, we work along side of the construction crews, so we are familiar with holding our own Safety meetings for supervisory personnel. These meetings are conducted on a weekly basis at a time and place to be designated by the Project/Program Manager or Construction Superintendent. These meetings shall be open to attendance by all subcontractor supervisors and all customer representatives. The Construction Superintendent shall be the official holder of the minutes of all such meetings.

- Safety Toolbox Meetings

Toolbox meetings (installation crews) were held on a schedule of one each week or more often if so directed by the Project Manager. These meetings are to be conducted by the Technician supervisor to review safety rules, issues and procedures. Results of these meetings shall be reported to the Project Manager or other delegated person with the responsibility of safety at the site.

- Safety Hard Hats / Reflective Vests

All shipyards and construction areas have be considered “hard hat” areas and the wearing of hard hats and reflective vests will be MANDATORY. All warehouse and cable yards will be considered hardhat areas. Only hard hats meeting standard acceptable to Heavy Construction Industry will be worn in the construction area.

- Signs and Posters

Safety literature has been distributed at Toolbox meetings and as deemed necessary or desirable. Safety bulletins will be posted at strategic locations on bulletin boards and educational and warning signs will were posted in accordance with needs. Safety films provided by customers will be shown where practical.

- Preventive Maintenance Inspection

Appropriate mechanical safety inspections are a part of the equipment preventive maintenance program and as such are the responsibility of both field and shop mechanical department supervisors. Records and reports are a part of the preventive maintenance program. Periodic spot check inspections may be made by, or at the order of, the appointed safety supervisor or other supervisory personnel delegated such responsibility.

- Motor Vehicles

All company vehicles were inspected on a schedule maintenance program. Vehicles found to be in an unsafe operating condition will be removed from service, repaired or replaced, and re-inspected before being placed in service again. No company vehicle will be driven at a speed greater than is reasonable and proper, with due regard for weather, traffic, intersections, width and character of the roadway, type of motor vehicle, and any other existing condition. The number of people in passenger-type vehicles will not exceed the number, which can be seated. All motor vehicles will be fully equipped with seat belts.

2.5 AREA OF CONSIDERATION 2 – MANAGEMENT PLAN

2.5a Subcontractor Plan

At Tavares, we have developed policies and procedures specifically for identifying and managing subcontractors, tracking subcontractor production, billing and payables. All of our subcontractors are required to complete subcontractor applications, follow our safety and quality standards and must demonstrate verifiable past perform, provide proof of insurance and workers compensation. These procedures ensure that we are:

- Providing minimum standard of service to our customers

- Eliminating non-performing subcontractors

- Delivering high quality output of work

- Able to meet the challenging demands of working in varying environments (remote locations, adverse conditions)

- Creating consistent payment standards

- Universal set of policies

- Maintain safe workplace standards

At any given time throughout a fiscal year, Tavares workload and ongoing projects range from twenty (20) projects to upwards of thirty (30) projects simultaneously. Each project can have anywhere between 2 to 15 subcontractors per job. Even though there may be some overlap for projects in close proximity or of similar scope more than 65% of our subcontractors are different firms. Without uniform systems it would be nearly impossible to manage such volume of work.

We have always paid our subcontractors throughout projects even when we were not paid by the owners as in the recent 2018/2019 case of our Easton Building Rehabilitation project.

On September 20, 2018 we were awarded a project by the Department of the Interior, National Park Services (NPS) to renovate the Northeast Region Headquarters Offices located at 15 State Street, Boston Massachusetts also known as the Easton Building. Shortly after we mobilized manpower to the site, built our HAZMAT containment, started abatement and began demolition the government shutdown.

As a non-DOD agency DOI and NPS were subject to being furloughed. So in one swoop instance all of the contracting staff and office personnel were no longer accessible via phone or email. One letter we received asked us to please continue working and ensured that we would be eventually paid once the matter was resolved. The NPS onsite supervisor continued working during that time opening/closing the building so that we could have access to the job site.

Even without confirmation of when Tavares could invoice for the progress work, we continued providing manpower, supplies and equipment to the job. Furthermore, we continued to pay all subcontractors invoices according to their normal billing cycle.

The project continued uninterrupted until things resumed back to business on January 25, 2019. Even after things resumed it would take weeks before anyone could catch up with the backlog of work. Tavares maintained its’ commitment to the project, National Park Service and to its’ subcontractors.

2.5b Integrate subcontractors into our organization

We understand that subcontractors are an integral part of the transactional process and we value their time, skill and commitment which is why often times we put them at the forefront often times before ourselves to be compensated. This strategy has allowed us to have access to crews even during the busiest construction seasons.

At the corporate level subcontractors are constantly in and out of our offices for inquiries, schedules, plans, billing, payments, submittals you name it. Tavares has approximately 7 administrators currently working in our corporate office that support it’s operations, management of the wide array of projects, subcontractors, managers and teams throughout New England.

On site we have Project Managers, Site Superintendents, Quality control members who are instrumental in making sure that the work whether performed by in-house staff or subcontractors meet client/specification/quality standards. This help ensure that proper billing occurs. Both from Tavares to the owner and also between the subcontractor and Tavares.

See attached Organization Chart – Exhibit #2

2.5c How own workforce “in house” will meet 15% requirements

The Tavares team will perform all the Construction Management functions to include holding weekly project meetings, document control, quality control, safety, submittals, site supervision, sub-contractor screening and review, security, scheduling, and all other GC administrative requirements these services will more than meet the contract requirements of 15% of GC. We plan to meet the Specialty Trades requirement in a number of ways, our team self-performs several specialty services such as project lay out, stud and dry wall installation, ceilings, doors, window and hardware installation, finishes, painting, some flooring and some concrete installation. When these services are self-performed, we will far exceed the 15% requirement in the contract documents.

Currently our current List of In-House Trade Employees include:

Rough Carpentry 	10 F/T

Painting 		6 F/T

Flooring 		3 F/T

Demolition 		12 F/T

Doors  			10 F/T

Ceilings  		3 F/T

2.5d Meet, sustain, grow workforce ramp up to support task orders

Tavares is a signature to the Union so we can easily grow our workforce as needed. Our union affiliations include:

- United Brotherhood of Carpenters and Joiners of America / New England Regional Council of Carpenters

- Massachusetts and Northern New England Laborers District Council of the Laborers’ International Union of North America

- Rhode Island Laborer’s District Council of the Laborer’s International Union of North America

- Massachusetts Painters and Allied Trades District Council No. 35

- Rhode Island Painters and Allied Trades District Council No. 11

For example, Tavares is a preferred minority vendor for Providence Schools. Each summer Tavares LLC is required to double its’ staff to meet the quick timeline and short notice requirements of fulfilling school board projects throughout RI and MA.

All of these projects have strict timelines with immovable completion dates. The continued issuance of ongoing school board work each year for the last 10 years evidences Tavares ability to meet the high stress requirements and deliver the manpower necessary to complete the projects on time.

2.5e Scheduling techniques and planning methodology

The team will develop a Schedule using such tools as Microsoft Projects, or Primavera to identify and define milestones, budgets, staffing requirements, and Bench Mark deliverables. During the development of the Schedule we will identify risk areas and associated levels of risk. A work breakdown structure (WBS) will be developed with specific tasks and subtasks, skill level requirements, knowledge needed and personnel. The detailed Project Schedule will be broken down by distinct project tasks, task will be linked by precedence, and the Critical Path will be shown.

Often times when deriving a schedule most teams strictly consider deliverables. But in the case where there are manufactured parts, components the schedule must consider fabrication timelines.

Using the seed project as an example. Let’s say the timeline for the fabrication of the light poles is 8 - 10 weeks. We must factor that into our submittal timeline, not just the actual installation time. Tavares would have to present the submittal material, have it stamped and approved 10 weeks prior to when we want to commence the installation. Meaning if the CO/COR has up to 4 weeks to turnaround submittals they must be submitted 14 weeks in advance to guarantee achieving substantial completion date.

Other factors to include are, the amount of time which concrete curing must occur to achieve the necessary PSI strength required to set the light poles. During the winter months, concrete requires longer period of time to achieve PSI. This sequence of events must be carefully considered to ensure timely sequential delivery of all materials.

2.5f Capacity and capability to propose on numerous task orders simultaneously

Tavares LLC is experienced at performing building upgrades, renovations and interior build outs that include energy reduction measures. Our project team has over 75 years of construction experience and will be led my Mr. Fernando Tavares.

Fernando Tavares managed a $50 million federal project as well as a $45 million project at the Providence Safety Complex as the Construction Executive. Mr. Tavares has also worked on a $150 million project at T.F. Green Airport as a Gilbane Building Company employee and a $40 million project at Logan International Airport. His responsibilities as Project Manager were demolition, trenching, concrete, doors/frames/hardware, and interior finishes.

Tavares daily Project Executive/Project Manager will be Mr. Chris Ferrant. Chris has managed airport projects at Logan International Airport for over 15 years. Chris has a complete understanding of high security protocol, such as completion of work within the environment of a full operational base, safety, badging/security clearance, scheduling, contractor coordination, protection, airside protocol, landside protocol, occupied spaces, deliveries, daily cleanup, and noise consideration.

Tavares Project Manager/Superintendent Mr. Jack Kowal has worked closely with Fernando Tavares for over 20 years. Prior to working with Tavares Mr. Kowal was a Project Superintendent/Project Manager for 20 years. Before becoming a Project Manager Jack worked at various airport and military projects with a single value over $50 million. Jack’s carpenter foreman skills allows him to really understand how a project is put together.

See attached Level of Responsibility Exhibit - #3

Tavares has multiple project executives, project managers, superintendents all certified OSHA 30, most certified U.S. Army Corps of Engineers Construction Quality Management. Each one individually can be deployed as needed throughout Region A of the 99th Readiness Division Area of Responsibility to propose on numerous task orders simultaneously and perform on subsequent awards in accordance with the negotiated completion dates.

As stated in 2.5a we currently have ongoing up to 30 projects simultaneously throughout the year, managing hundreds of subcontractors. Our seven (7) in house administrative Team coupled with our existing system can absorb the additional responsibilities.

2.5 Area of Consideration 3 – Bonding Capacity

See attached letter of verification – Exhibit 1